## Dashboard
Xenovaa Chat — Task Tracker
Generated | 08 Sept 2026
Summary
Completed | 34
In Progress | 1
Pending | 6
Blocked | 0
Total tasks | 41
% Complete
Legend
Completed
In Progress
Pending
Blocked

## Tasks
# | Phase | Task | Description | Status | Notes
1 | Phase 1 — Foundation | Project scaffolding | React (Vite) + Tailwind frontend, Express + Socket.IO backend | Completed
2 | Phase 1 — Foundation | Supabase schema & migrations | Initial schema (users, departments, conversations, messages, etc.) | Completed
3 | Phase 1 — Foundation | JWT authentication | Register / login / get current user, bcrypt password hashing | Completed
4 | Phase 1 — Foundation | Departments CRUD (backend) | Admin-only writes, public read (needed pre-login) | Completed
5 | Phase 1 — Foundation | Login & Register pages | Auth screens with validation and error states | Completed
6 | Phase 2 — Users & Requests | Employee directory | Search + department filter, excludes self/inactive | Completed
7 | Phase 2 — Users & Requests | User profile page | View another employee, relationship-aware actions | Completed
8 | Phase 2 — Users & Requests | Chat requests | Send / accept / reject / cancel, enforced server-side | Completed
9 | Phase 2 — Users & Requests | Notifications system | Backend notification model + REST endpoints | Completed
10 | Phase 2 — Users & Requests | Notification bell UI | Live unread badge, dropdown, click-through routing | Completed
11 | Phase 3 — Real-Time Chat | Presence tracking | Online/offline via Socket.IO, multi-tab safe | Completed
12 | Phase 3 — Real-Time Chat | Real-time messaging | send_message / receive_message over Socket.IO | Completed
13 | Phase 3 — Real-Time Chat | Typing indicator | typing_start/typing_stop, animated dots in UI | Completed
14 | Phase 3 — Real-Time Chat | Delivered / read receipts | Per-recipient status, live updates | Completed
15 | Phase 3 — Real-Time Chat | Conversations REST + Chats UI | History, sidebar list, unread counts | Completed
16 | Phase 4 — Rich Messaging | Image/file upload & sharing | Multer + Supabase Storage, type/size validation | Completed
17 | Phase 4 — Rich Messaging | Reply to message | Quoted preview resolved server-side | Completed
18 | Phase 4 — Rich Messaging | Pin / unpin messages | Pinned-messages bar, live sync across users | Completed
19 | Phase 4 — Rich Messaging | Delete for me / for everyone | Placeholder for all vs. per-user hide | Completed
20 | Phase 5 — Groups & Safety | Block / unblock users | Enforced on every message send, not just requests | Completed
21 | Phase 5 — Groups & Safety | Group chat creation | Create with multiple members, no request needed | Completed
22 | Phase 5 — Groups & Safety | Group management | Add/remove members, promote/demote admin, leave | Completed
23 | Phase 5 — Groups & Safety | Blocking enforcement | Direct messages blocked both ways; groups unaffected | Completed
24 | Phase 6 — Admin & Company | Reports | Report a message/user; admin list + resolve/dismiss | Completed
25 | Phase 6 — Admin & Company | Admin user management | Activate/deactivate, change role, self-protection | Completed
26 | Phase 6 — Admin & Company | Admin department management UI | Create/rename/delete departments from dashboard | Completed
27 | Phase 6 — Admin & Company | Usage stats dashboard | Users, messages, conversations, groups, open reports | Completed
28 | Phase 6 — Admin & Company | Company-wide announcements | Admin post, live banner, per-user notification | Completed
29 | Phase 7 — UI/UX Polish | Design system & color palette | Tokenized theme applied consistently across all screens | Completed
30 | Phase 7 — UI/UX Polish | Sidebar navigation redesign | Slack/Linear-style layout replacing top nav bar | Completed
31 | Phase 7 — UI/UX Polish | Light / Dark / System theme toggle | User-selectable, persisted, no flash on load | Completed
32 | Phase 8 — Enhancements | Admin instant chat-start | Admins message anyone without approval; blocking still applies | Completed
33 | Phase 8 — Enhancements | Profile picture upload/update/remove | Public avatars bucket, 5MB limit, validated types | Completed
34 | Open Items | Backend/frontend port alignment | Backend moved to 5001; frontend defaults updated to match | Completed | Resolved during this session
35 | Open Items | Local dev server stability | Dev servers were OOM-killed under low system memory | Pending | Needs free RAM on the dev machine, not a code issue
36 | Open Items | chat-uploads bucket privacy | Bucket is public; app only ever uses signed URLs for it | Pending | Low risk — decide whether to switch to private
37 | Open Items | Test data cleanup in Supabase | Alice/Bob/Carol test accounts + test group/department | Pending | Awaiting go-ahead to delete
38 | Future / Not Started | "Break" presence status | StatusDot now renders a break state; backend enum/logic TBD | In Progress | Started outside this session — needs backend support
39 | Future / Not Started | @mentions in group chats | Notification type exists in schema, not yet wired up | Pending
40 | Future / Not Started | Admin "create user" flow | Currently only self-registration exists | Pending
41 | Future / Not Started | Live-kick deactivated users' sockets | Access is blocked on next request, not mid-session | Pending